## Summary
Boardsmith Feature User Story Ledger | Boardsmith Feature User Story Ledger | Boardsmith Feature User Story Ledger | Boardsmith Feature User Story Ledger | Boardsmith Feature User Story Ledger | Boardsmith Feature User Story Ledger
Generated | 2026-06-24
Canonical tracker | C:/dev/boardsmith/docs/qa/boardsmith-feature-user-story-ledger.xlsx
Total stories | 62
Pending test stories | 0
Failed test stories | 0
Fixed stories | 0
Retest pass stories | 62
Known errors | 62
Workflow | Workflow | Workflow | Workflow | Workflow | Workflow
1 | Inventory every feature from code/docs/tests.
2 | Run automated verification and exploratory browser QA.
3 | Document every error in Feature Stories and Testing Log.
4 | Fix logistical or UX errors with narrow changes.
5 | Retest changed and affected user behaviors post-fix.

## Feature Stories
ID | Area | Feature | User Story | Expected Behavior | Source Of Truth | Critical Edge Cases | Verification Coverage | Current Status | Test Pass Status | Errors Found | Fix Status | Retest Status | Last Updated
BS-US-001 | Access | Private access gate | As a private MVP user, I can enter the configured access password and return to the page I asked for. | When BOARDSMITH_ACCESS_PASSWORD is set, protected routes redirect to /access; a correct password sets an HTTP-only cookie and redirects to sanitized returnTo; wrong passwords do not set access. | app/access/page.tsx; app/access/verify/route.ts; lib/access/private-access.ts | Wrong password, missing returnTo, unsafe returnTo, public access paths. | access-page.test.ts; access-verify-route.test.ts; private-access-gate.test.ts; private-access-proxy.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-002 | Navigation | Application shell navigation | As a user, I can move between Dashboard, My Projects, New Project, and Settings from the app shell. | Root layout exposes stable links and preserves private workspace framing without public sharing/export claims. | app/layout.tsx | Route availability, active context, no public product terminology. | dashboard-page.test.ts; settings-page.test.ts; e2e/smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-003 | Settings | Private MVP settings posture | As an owner, I can see whether OpenAI and storage are configured and what capabilities are intentionally deferred. | Settings reports OpenAI configured/missing, Supabase/local JSON storage, private access posture, planning-aid boundary, no sharing/export/auth promises. | app/settings/page.tsx | Missing env vars, Supabase mode, deferred features copy. | settings-page.test.ts; supabase-config.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-004 | Dashboard | Workspace overview | As an owner, I can see project counts, recent projects, latest update, and next actions from the dashboard. | Dashboard sorts recent projects by update, shows empty state when none exist, and never introduces public sharing or export language. | app/page.tsx | No projects, failed generation, archived hidden from active summaries, built projects. | dashboard-page.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-005 | Dashboard | Idea draft entry point | As a user with a rough idea, I can draft setup fields from the dashboard without saving a project yet. | Dashboard posts idea_text to /projects/draft; short ideas redirect to invalid_idea; successful drafts return to /projects/new?draft=idea with a short-lived cookie. | app/page.tsx; app/projects/draft/route.ts; lib/projects/natural-language-intake.ts | Short idea, safety-blocked idea, unsupported idea, cookie draft preservation. | natural-language-intake.test.ts; project-form-routes.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-006 | Dashboard | Starter shortcuts | As a new user, I can start from curated beginner examples. | Dashboard starter links open /projects/new?example=... and the new-project page pre-fills editable starter fields when the slug is known. | app/page.tsx; app/projects/new/page.tsx; lib/projects/intake-examples.ts | Unknown example, editable starters, no auto-save. | dashboard-page.test.ts; project-form-routes.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-007 | Project Intake | New project form sections | As a user, I can enter project type, skill, size, material, mounting context, tools, and notes before any plan is generated. | The form posts structured fields to /projects/create and uses schema validation for required title, type, skill, dimensions, thickness, material, tools, and intended use. | app/projects/new/page.tsx; lib/projects/types.ts | Missing fields, invalid numbers, no tools, simple shelf height defaulting to material thickness. | project-form-routes.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-008 | Project Intake | Natural-language supported draft | As a user, I can paste a clear supported shelf idea and review conservative generated setup fields before saving. | Supported drafts prefill form fields, show review metadata, keep structured fields editable, and do not save or generate a plan until submit. | app/projects/draft/route.ts; app/projects/new/page.tsx; lib/projects/natural-language-intake.ts | Store-cut preference, support count, heavy-load notes, missing-field hints. | natural-language-intake.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-009 | Project Intake | Concept-only or unsupported draft resolution | As a user, I cannot accidentally save an unsupported idea as a build packet without explicitly choosing a supported template. | Concept-only and unsupported natural-language drafts require draft_resolution=supported_template_selected before create; otherwise redirect back with unresolved_idea. | app/projects/create/route.ts; app/projects/new/page.tsx | Unsupported woodworking-adjacent ideas, unrelated non-woodworking ideas, checkbox missing. | natural-language-intake.test.ts; project-form-routes.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-010 | Project Intake | Safety-blocked draft protection | As a user, I am blocked from saving safety-sensitive natural-language drafts as build setups. | Blocked natural-language drafts redirect to blocked_idea and preserve draft review notes; createProject is not called. | app/projects/create/route.ts; app/projects/new/page.tsx; lib/projects/natural-language-intake.ts | Cribs, ladders, seating, overhead storage, child sleep/climbing hazards. | natural-language-intake.test.ts; clarification-gate.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-011 | Project Intake | Draft preservation on invalid create | As a user, I do not lose entered setup fields after submitting invalid intake. | Invalid intake redirects to /projects/new?error=invalid_intake and stores the attempted draft in a short-lived HTTP-only cookie. | app/projects/create/route.ts; lib/projects/intake-draft.ts | Schema errors, natural-language draft metadata preservation, cookie max age. | project-form-routes.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-012 | Project Intake | Shelf layout inputs | As a shelf planner, I can specify single shelf, separate shelves, or connected unit plus count, spacing, and height. | Shelf layout fields are only persisted for simple_shelf projects; multi-shelf layouts require valid count where routes enforce it. | app/projects/new/page.tsx; app/projects/[id]/shelf-layout/route.ts; lib/projects/types.ts | Missing count, impossible connected-unit height, separate shelves should not fail connected-unit height checks. | project-shelf-layout-route.test.ts; shelf-layout-validation tests; readiness-friction e2e | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-013 | Project Intake | Mounting and safety context capture | As a wall-shelf user, I can capture mounting method, wall type, stud access, load, moisture, location, support count, risk spots, and obstructions. | The form serializes these fields into managed Structured Intake text that downstream deterministic adapters can parse. | app/projects/new/page.tsx; lib/projects/types.ts; lib/projects/managed-intake-sections.ts; lib/projects/project-intake-signals.ts | Not sure values, not wall mounted, bathroom humidity, heavy load, support count. | managed-intake-sections.test.ts; project-intake-signals.test.ts; create-build-model-draft.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-014 | Project Intake | High-risk spot exclusivity | As a user, I can select risk spots without contradictory none/not-sure combinations. | Checking none_of_these or not_sure clears other risk spots; selecting a concrete risk clears the exclusive values. | app/projects/new/ProjectIntakeFormEnhancements.tsx | Multiple clicks, form change events, persisted default checked values. | Not directly covered | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-015 | Project Intake | Quick-select basic tools | As a beginner, I can quickly select basic layout and safety tools. | The quick-select button checks tape measure, pencil, level, and safety glasses, then updates live form summary. | app/projects/new/ProjectIntakeFormEnhancements.tsx; app/projects/new/ProjectIntakeLiveSummary.tsx | Button outside expected form, repeated clicks, summary update. | e2e/readiness-friction.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-016 | Project Intake | Live review summary | As a user, I can see missing required info and later review items before saving. | Client summary updates on input/change, lists missing title/dimensions/thickness/material/tools, review items, readiness chips, and submit label. | app/projects/new/ProjectIntakeLiveSummary.tsx | Required vs review-only, measurement confidence, heavy load, no tools. | e2e/readiness-friction.spec.ts partially | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-017 | Project Intake | Create project | As a user, I can save a valid setup and land on the project detail page. | Create route parses form data, calculates safety flags through storage, revalidates dashboard/list, clears draft cookie, and redirects to /projects/[id]. | app/projects/create/route.ts; lib/storage/project-store.ts; lib/safety/safety-review.ts | Invalid intake, natural-language resolution, local/Supabase persistence. | project-form-routes.test.ts; project-store.test.ts; project-store-supabase-rpc.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-018 | Project List | Project library filters | As a user, I can search and filter projects by text, archive state, type, status, plan state, and record state. | Projects page sorts by updated_at/created_at/title, applies archive filter first, and displays clear filter summaries and no-results states. | app/projects/page.tsx | Archived filter, built status, no plan, notes/build-log record, invalid query values. | project-list-page.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-019 | Project List | Project list actions and badges | As a user, I can open, print, review records, archive, or restore from each project row based on state. | Cards show next-step label, status strip, generated plan count, notes/build-log indicators, print link only when a plan exists, archive or restore action. | app/projects/page.tsx | Archived, built, failed generation with/without plan, no generated plan. | project-list-page.test.ts; project-archive-route.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-020 | Project List | List-level success and error feedback | As a user, I see non-technical list messages when archive/restore or route errors occur. | Known error query strings map to friendly copy; archive/restored query flags show green confirmation. | app/projects/page.tsx; lib/projects/project-list-errors.ts | Unknown errors, not found, already archived/not archived. | project-list-errors.test.ts; project-list-page.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-021 | Project Detail | No-plan detail state | As a user, I can review saved intake, readiness, template guidance, notes, and generate action before any plan exists. | Detail page builds no-plan snapshot from template/build model, shows recommended next step, readiness gate, intake, review triggers, empty plan state, and record section. | app/projects/[id]/page.tsx; lib/plans/gated-build-packet-snapshot.ts | Unsupported/concept-only, archived, missing dimensions, no template hint. | project-detail-build-model.test.ts; project-planning-lifecycle.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-022 | Project Detail | Clarification gate | As a user, I see targeted questions before generation when important details are missing or unsafe. | Clarification gate returns ready/needs_details/blocked/concept/unsupported states, shows answerable questions, and blocks generation when not ready. | lib/projects/clarification-gate.ts; app/projects/[id]/page.tsx | Heavy shelves, bathroom humidity, raised planter support, child/electrical, unsupported ideas. | clarification-gate.test.ts; project-planning-lifecycle.test.ts; e2e/readiness-friction.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-023 | Project Detail | Clarification answer update | As a user, I can answer readiness questions and save them back to Project Intake without creating a plan version. | Clarification route validates answerable fields, updates structured intake/managed sections, revalidates detail, and redirects with clarification_status. | app/projects/[id]/clarification/route.ts; lib/projects/clarification-answer-loop.ts | Empty answers, archived project, missing schema columns, next readiness status. | clarification-answer-loop.test.ts; project-clarification-route.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-024 | Generation | Generate plan command | As a user, I can generate a plan only when the project lifecycle allows it. | Generate route checks archived state, clarification gate, shelf-layout blockers, then drafts build model, calls structured OpenAI generation, validates, saves latest plan. | app/projects/[id]/generate/route.ts; lib/projects/project-planning-lifecycle.ts | Archived, clarification_gate, missing/invalid shelf layout, OpenAI failure, deterministic quality failure. | generate-route-feedback.test.ts; generation-feedback.test.ts; generate-project-plan.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-025 | Generation | Generation failure feedback | As a user, I get specific repair guidance when generation is blocked or fails. | Known failure reasons render non-technical panels and next actions; archived saves do not mark failed; deterministic failures are safe. | lib/ai/generation-feedback.ts; app/projects/[id]/page.tsx | Missing API key, validation/quality failures, archived stale save, impossible shelf height. | generation-feedback.test.ts; generate-route-feedback.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-026 | Plan Packet | Core packet order | As a user, I can read a generated plan in the expected packet order. | Detail plan order is Build Snapshot, Hero Visual, Project Visuals / Diagrams, Check Before Building, Materials and Parts, Cut Checklist, Buying Plan, Build Guide, Reference Review Notes. | app/projects/[id]/page.tsx; lib/plans/printable-plan-packet.ts | No generated plan, unresolved dimensions, mobile horizontal cut table. | plan-packet-contract.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-027 | Plan Packet | Hero visual and diagrams | As a builder, I can see deterministic visuals that reflect structured build data rather than prose. | Wall shelf and planter visuals use deterministic view models/renderers and safe fallbacks when geometry is missing. | app/projects/[id]/PlanPacketSections.tsx; app/projects/[id]/WallShelfDiagrams.tsx; app/projects/[id]/PlanterBoxCutDiagram.tsx; lib/plans/*diagram* | Missing dimensions, invalid multi-shelf height, unresolved support/frame, print compatibility. | wall-shelf-diagrams-render.test.ts; wall-shelf-diagram-view-model.test.ts; planter-box-packet-view-models.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-028 | Plan Packet | Material summary | As a user, I can review primary materials, hardware, finish supplies, and assumptions before buying. | Material summary groups plan/build-model materials and shows calm review notes when material data is missing or vague. | lib/plans/material-summary.ts; app/projects/[id]/page.tsx | Missing material, hardware placeholders, finish-only notes. | material-summary.test.ts; printable-plan-manifest.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-029 | Plan Packet | Cut list review | As a user, I can verify piece counts, dimensions, material, duplicates, and missing measurements before cutting. | Cut-list review reconciles generated cuts and build-model pieces, flags missing/unresolved/placeholder dimensions, duplicate-looking rows, and unsafe cutting states. | lib/plans/cut-list-review.ts; app/projects/[id]/page.tsx | Empty generated cut list, duplicate pieces, unresolved dimensions, suspicious quantity. | cut-list-review.test.ts; printable-plan-manifest.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-030 | Plan Packet | Plan review and export readiness | As a user, I can see plan quality and future-output readiness without mistaking it for an export feature. | Plan Review and Export Readiness summarize deterministic warnings/blockers and explicitly avoid app-generated PDF/CAD/DXF promises. | lib/plans/plan-quality.ts; lib/plans/export-readiness.ts; app/projects/[id]/page.tsx | Derived build model, limited confidence, unsupported output candidates. | plan-quality.test.ts; export-readiness.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-031 | Plan Packet | Action checklist | As a user, I get prioritized review actions before buying, cutting, mounting, or building. | Checklist derives required/review/optional actions from safety, mounting, hardware, material, cut-list, and unresolved questions with planning-aid copy. | lib/plans/plan-action-checklist.ts; app/projects/[id]/PlanActionChecklist.tsx | Hardware-only unknowns, child/outdoor/load triggers, no specific signals. | plan-action-checklist.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-032 | Plan Packet | Advanced project details | As a user, I can inspect intake, template guidance, build model, plan review, history, and records without cluttering the primary packet. | Advanced details are in a disclosure once a plan exists and include actions, nav, intake, triggers, template guidance, build model, review panels, tweak, comparison, history, and records. | app/projects/[id]/page.tsx | Disclosure content order, archived projects, no latest plan. | project-detail-build-model.test.ts; print-preview-page.test.ts partially | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-033 | Plan History | Plan versions and comparison | As a user, I can compare the latest plan with older versions and understand practical changes. | Saved plans are versioned, latest is selected deterministically, older versions can be compared with calm no-change copy. | lib/plans/plan-comparison.ts; app/projects/[id]/page.tsx; lib/storage/project-store.ts | Only one version, latest-attempt failed with saved plan, older plan selected by query. | plan-comparison.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-034 | Revision | Direct plan revision | As a user, I can request a safe prose-only plan tweak and receive a new saved version. | Revision route normalizes input, requires latest plan, classifies intent, calls revised structured generation, saves new latest plan, and redirects to comparison. | app/projects/[id]/revise/route.ts; lib/plans/revision-intent.ts | Empty, too long, no plan, archived, generation failure. | tweak-plan-route.test.ts; revision-intent.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-035 | Revision | Structured revision intake patch | As a user, I can request safe explicit dimension/material/layout changes and have Project Intake updated before regeneration. | Width, depth, material, material thickness, shelf layout/count/spacing requests patch structured intake and do not create a plan version. | app/projects/[id]/revise/route.ts; lib/projects/project-intake-revision.ts | Unparseable structured request, stale archive during update, clarification status after patch. | tweak-plan-route.test.ts; project-intake-revision.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-036 | Revision | Blocked revision categories | As a user, I am redirected away from unsafe or ambiguous revision requests instead of getting an untrustworthy plan. | Support/mounting approvals, cut-list requests, safety-sensitive, ambiguous, unsupported, and mixed unsafe requests are blocked or redirected with category labels. | lib/plans/revision-intent.ts; app/projects/[id]/revise/route.ts | Mixed safety and structured, vague structural changes, support claims. | revision-intent.test.ts; tweak-plan-route.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-037 | Project Record | Project notes | As a user, I can save private notes on a project without affecting generated plans. | Notes route saves plain text up to schema limit, redirects with success, blocks archived/stale archived writes. | app/projects/[id]/notes/route.ts; lib/storage/project-store.ts | Missing project, archived, stale archived no-op, storage failure. | project-notes-route.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-038 | Project Record | Build log | As a user, I can record completion, actual material, changes, and lessons learned. | Build-log route parses checkbox/date/text fields, updates project record, redirects with success, and blocks archived writes. | app/projects/[id]/build-log/route.ts; lib/projects/types.ts; lib/storage/project-store.ts | Blank date, completed true/false, archived, schema bounds. | project-build-log-route.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-039 | Project Lifecycle | Duplicate project | As a user, I can duplicate a project setup without copying generated plan history. | Duplicate route copies intake as a fresh draft, preserves no generated plans/history, blocks archived sources, redirects to the duplicate detail. | app/projects/[id]/duplicate/route.ts; lib/storage/project-store.ts | Source missing, archived/stale archived, Supabase duplicate fields. | duplicate-project-route.test.ts; project-store.test.ts; project-store-duplicate-supabase.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-040 | Project Lifecycle | Archive project | As a user, I can hide inactive projects without deleting their data or plans. | Archive sets archived_at, hides from active list/dashboard, preserves generated plans/records, blocks repeat archive, and revalidates routes. | app/projects/[id]/archive/route.ts; lib/projects/project-planning-lifecycle.ts; lib/storage/project-store.ts | List vs detail return_to, already archived, missing project, storage failure. | project-archive-route.test.ts; project-planning-lifecycle.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-041 | Project Lifecycle | Restore project | As a user, I can return an archived project to the active workspace. | Restore clears archived_at, returns to active list/detail based on return_to, blocks restore on active projects. | app/projects/[id]/restore/route.ts; lib/projects/project-planning-lifecycle.ts; lib/storage/project-store.ts | Archived-list return, active project, missing project, stale no-op. | project-archive-route.test.ts; project-planning-lifecycle.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-042 | Project Lifecycle | Archived read-only state | As a user, I can review archived project data but cannot generate, revise, duplicate, save notes, save build log, or update shelf layout until restored. | Lifecycle gates project write/revision/generation/archive/restore commands and detail UI shows read-only archived project actions. | lib/projects/project-planning-lifecycle.ts; app/projects/[id]/page.tsx | Existing print remains available, stale writes after archive, restore re-enables writes. | project-planning-lifecycle.test.ts; notes/build-log/shelf-layout/duplicate/generate/tweak route tests | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-043 | Print | Print route empty state | As a user, I cannot print a build sheet before a generated plan exists. | Print route loads latest plan snapshot; if no generated plan, it renders an empty state with back link and generation reminder. | app/projects/[id]/print/page.tsx | Missing project, no plan, derived no-plan manifest. | print-preview-page.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-044 | Print | Browser print packet | As a user, I can open a clean browser-print build sheet from the same structured manifest as detail. | Print route includes packet sections, print button, no-print controls, shop notes on print, and explicit no PDF/CAD/CNC/export/download copy. | app/projects/[id]/print/page.tsx; app/projects/[id]/print/PrintDialogButton.tsx | window.print behavior, mobile table, section order, archived existing plans. | print-preview-page.test.ts; printable-plan-manifest.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-045 | Templates | Supported project types | As a user, I can choose door hanger, layered cutout, wood sign, wall shelf, or planter box templates. | Each declared project type has labels, template hints, and a supported build-model drafting adapter; unsupported types are rejected. | lib/projects/types.ts; lib/templates/template-hints.ts; lib/build-model/supported-project-type-drafting.ts | Adapter coverage drift, unsupported type rejection. | create-build-model-draft.test.ts; template hint tests via generation prompt | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-046 | Templates | Wall shelf single-shelf golden path | As a shelf builder, I get a coherent single-shelf packet with consistent part labels, visuals, buying plan, cut layout, readiness, and build guide. | Wall-shelf typed view models assign deterministic Part A, safe hardware placeholders, store-trip minimums, diagram/cut/buying/readiness/build-guide sections. | lib/plans/wall-shelf-*; app/projects/[id]/WallShelf*.tsx | Missing support details, selected visible brackets, print-safe labels. | wall-shelf-* tests; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-047 | Templates | Wall shelf separate shelves | As a user planning multiple separate shelves, I see repeated assemblies rather than an invented connected unit. | Separate-shelf layout scales shelf boards/support placeholders by count and does not use connected-unit copy. | lib/diagrams/wall-shelf-diagram-model.ts; lib/plans/wall-shelf-* | Multiple separate shelves, support count, impossible-height false positives. | wall-shelf-diagrams-render.test.ts; create-build-model-draft.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-048 | Templates | Wall shelf connected unit review | As a user planning a connected shelf unit, I see support/frame review until side supports or frame pieces are modeled. | Connected units without modeled supports render needs_review, avoid freestanding assembly instructions, and do not assign invented support part labels. | lib/plans/wall-shelf-*; lib/projects/shelf-layout-validation.ts | Unresolved support/frame, modeled support pieces present, print-safe copy. | wall-shelf-* tests; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-049 | Templates | Wall shelf invalid height protection | As a user, I am blocked or shown review state when a connected shelf unit cannot physically fit the requested count and board thickness. | Impossible height is flagged before generation and in view models; trusted complete diagrams/build guide are not rendered for invalid height. | lib/projects/shelf-layout-validation.ts; lib/plans/wall-shelf-* | Separate shelves excluded, stale invalid plans, missing count. | safety-review.test.ts; generate-route-feedback.test.ts; wall-shelf-* tests | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-050 | Templates | Wall shelf support and buying guidance | As a user, I get board-count, stock-length, bracket/support-count, fastener, wall, and finish review guidance without exact purchase claims. | Buying plan shows store-trip minimum, selected mounting method, intake/model support counts, exact retail stock caveat, and no vendors/prices. | lib/plans/wall-shelf-stock-board-view-model.ts; app/projects/[id]/WallShelfBuyingPlan.tsx | Visible L brackets, hidden brackets, not sure, heavy loads, humidity. | wall-shelf-stock-board-view-model.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-051 | Templates | Planter box packet | As a planter user, I get a review-first panel, drainage, liner, finish, stock/material, and connection planning packet. | Planter typed packet has Part A-E panel identity, cut layout, buying plan, readiness actions, and Build Guide without overclaiming supports/raised frames. | lib/plans/planter-box-*; app/projects/[id]/PlanterBox*.tsx | Raised planter support ideas, outdoor exposure, drainage/liner/fasteners. | planter-box-packet-view-models.test.ts; planter-box-part-schedule-view-model.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-052 | Safety | Deterministic safety review | As a user, I get conservative review flags for wall mounting, child/baby use, load, electrical, outdoor, missing dimensions, and material thickness. | Safety flags are calculated deterministically before generation and stored with the project. | lib/safety/safety-review.ts; lib/storage/project-store.ts | Electrical exclusions, light-weight wording, wall shelves, toddler ledges, impossible shelf dimensions. | safety-review.test.ts; project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-053 | Safety | Unsupported and high-risk idea handling | As a user, I get concept-only or blocked guidance for unsupported and high-risk projects instead of fake build packets. | Clarification/natural-language logic blocks high-risk ideas and keeps unsupported woodworking-adjacent ideas concept-only or unsupported. | lib/projects/natural-language-intake.ts; lib/projects/clarification-gate.ts; lib/projects/concept-brief.ts | Bookcases/cabinets, unrelated ideas, ladders, seating, cribs, overhead storage. | natural-language-intake.test.ts; clarification-gate.test.ts; concept-brief.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-054 | Storage | Local JSON persistence | As a developer/private user, I can use local JSON storage when Supabase is not configured. | Project store reads/writes .data/boardsmith.json or BOARDSMITH_DATA_FILE, sorts projects, preserves plans, and blocks stale archived writes. | lib/storage/project-store.ts | Missing file, duplicate, notes/build log, archive/restore, stale writes. | project-store.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-055 | Storage | Supabase private MVP persistence | As a hosted private MVP, Boardsmith can use server-only Supabase service-role persistence without public access. | Supabase mode requires URL and service role key, migrations keep private grants, generated plan saves use atomic RPC/latest-plan behavior. | lib/storage/project-store.ts; supabase/migrations | Service-role required, anon reserved, latest-plan uniqueness, archived save guard, schema drift. | supabase-config.test.ts; supabase-migrations.test.ts; project-store-supabase-rpc.test.ts; project-store-duplicate-supabase.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-056 | Plan Data | Generated plan schema validation | As a user, only schema-valid generated JSON can be saved as a plan version. | Generated plan parser validates dimensions, materials, cuts, steps, safety notes, assumptions, confidence, markdown, and plan metadata. | lib/plans/plan-schema.ts; lib/ai/generate-project-plan.ts | Invalid JSON, missing required safety notes, overlong/missing fields. | plan-schema.test.ts; generate-project-plan.test.ts; generate-route-feedback.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-057 | Plan Data | Build Model validation | As a user, structured build-model data stays internally consistent before it drives packet outputs. | Build Model schema validates ids and semantics such as piece/hardware/operation references before strict parsing accepts it. | lib/build-model/build-model-schema.ts; lib/build-model/create-build-model-draft.ts | Missing referenced pieces/hardware, unstable ids, nullable dimensions. | build-model-schema.test.ts; create-build-model-draft.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-058 | Plan Data | Deterministic plan quality checks | As a user, plan output is rejected or warned when it conflicts with structured project/build-model truth. | Quality checks validate project type, bounded dimensions, safety warnings, cut-list material/piece alignment, and overconfident safety claims. | lib/plans/plan-quality.ts; app/projects/[id]/generate/route.ts | Project-type mismatch, unbounded dimensions, missing required warnings, load-rated/certified copy. | plan-quality.test.ts; generate-route-feedback.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-059 | Plan Data | Printable plan manifest | As a user, detail and print views use the same structured manifest for packet content. | Manifest gathers project, generated plan, build model, materials, cut list, review, diagrams, action checklist, and disclaimers. | lib/plans/printable-plan-manifest.ts; app/projects/[id]/page.tsx; app/projects/[id]/print/page.tsx | Older plans without build_model_json, no-plan snapshot, wall shelf/planter variants. | printable-plan-manifest.test.ts; gated-build-packet-snapshot.test.ts; e2e/packet-smoke.spec.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-060 | Hosted Smoke | Hosted smoke script | As a maintainer, I can run a no-dependency hosted route/content smoke check without leaking secrets. | Smoke script supports Vercel bypass headers, optional storage-state cookie, expected text sentinel, redacts secrets, and fails clearly for login blockers. | scripts/hosted-smoke-check.mjs | Missing bypass secret, missing storage state, login redirect, expected text missing. | hosted-smoke-check-script.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-061 | Errors | Detail error mapping | As a user, I see stable non-technical errors for project detail route failures. | Known detail error codes render friendly panels without raw exceptions. | lib/projects/project-detail-errors.ts; app/projects/[id]/page.tsx | Notes/build-log/shelf-layout/generation/archive/duplicate failures, schema missing. | project-detail-errors.test.ts; route tests | Ready | Pass |  | No fix needed | Pass | 2026-06-24
BS-US-062 | Security | No forbidden product surfaces | As the owner, I do not see public sharing, marketplace, payments, vendor purchasing, CAD, CNC, PDF export, or load-certification features appear accidentally. | Docs and UI keep deferred surfaces explicit and avoid CTA/functionality for forbidden features unless explicitly approved. | AGENTS.md; docs/ARCHITECTURE.md; docs/VISION.md; app pages | Copy drift, generated plan copy, print route copy, e2e body text. | dashboard-page.test.ts; e2e/packet-smoke.spec.ts; plan-quality.test.ts | Ready | Pass |  | No fix needed | Pass | 2026-06-24

## Testing Log
ID | Pass | Command Or Scenario | Status | Errors Found | Evidence / Notes | Last Updated
TL-001 | Baseline verification | npm test | Pass |  | 62 Vitest files passed, 464 tests passed. | 2026-06-24
TL-002 | Baseline verification | npm run lint | Pass |  | ESLint passed after removing temporary builder artifact from output/. | 2026-06-24
TL-003 | Baseline verification | npm run typecheck | Pass |  | TypeScript passed after clearing stale .next generated route types. | 2026-06-24
TL-004 | Baseline verification | npm run build | Pass |  | Next production build passed. | 2026-06-24
TL-005 | Baseline verification | npm run test:e2e | Pass |  | Playwright e2e passed: 10 tests, including packet, readiness, smoke, and user-story-ledger flows. | 2026-06-24
TL-006 | Exploratory browser QA | First-time supported wall shelf flow | Pass |  | Covered by user-story-ledger e2e: dashboard idea draft opens the review form before save. | 2026-06-24
TL-007 | Exploratory browser QA | Heavy garage wall shelf readiness flow | Pass |  | Covered by readiness-friction e2e: heavy garage shelf support-count gate. | 2026-06-24
TL-008 | Exploratory browser QA | Raised planter boundary flow | Pass |  | Covered by readiness-friction e2e: raised planter support-template boundary. | 2026-06-24
TL-009 | Exploratory browser QA | Generated packet review/print seeded flow | Pass |  | Covered by packet-smoke e2e: seeded planter, wall shelf, separate shelves, connected unit, and print routes. | 2026-06-24
TL-010 | Post-fix verification | Retest changed user stories after fixes | Pass |  | No app logistical or UX defects remained after test-selector fixes; full e2e retest passed. | 2026-06-24